## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION XII - SOCCSSARGEN |  | CALENDAR YEAR: | 2026
PROVINCE: | SARANGANI |  | QUARTER: | 3
CITY/MUNICIPALITY: | GLAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects)
Fencing of GIT Compound, Phase II, Brgy. Calabanit | Brgy. Calabanit | 5000000 |  |  | 0% |  |  | Surveyed; DED Preparation
Completion of Barangay Health Station, Brgy. Tapon | Brgy. Tapon | 700000 |  |  | 0% |  |  | Scheduled for bidding on May 6, 2025
Completion of Barangay Health Station, Brgy. Congan | Brgy. Congan | 700000 |  |  | 0% |  |  | Scheduled for bidding on May 6, 2025
Redevelopment of Plaza and Parks, Barangay Poblacion | Barangay Poblacion | 2000000 |  |  | 0% |  |  | preparation for Master Plan
Renovation of 10 units Isolation Room @RHU Compound, Brgy. Poblacion | Barangay Poblacion | 1000000 |  |  | 0% |  |  | approval of Plan from DOH
Construction of Breastfeeding Room @RHU Compound, Brgy. Poblacion | Barangay Poblacion | 750000 |  |  | 0% |  |  | scheduled for bidding
Purchase of Land ( Relocation Site and other Incidental Fees) |  | 5000000 |  |  | 0%
Construction of Sanitary Landfill, Phase II, Brgy. Mudan | Brgy. Mudan | 5000000 |  |  | 0% |  |  | scheduled for survey
Total Social Development Project |  | 20150000 |  |  | 0 | 0
Economic Development (pls list down specific projects)
Debt Services |  | 30094908.67 |  |  | 13.75% | 4138898.37
Construction of Lined Canal (Junction NHW Purok Ostique) Phase II, Barangay Big Margus | Barangay Big Margus | 1000000 |  |  | 0% |  |  | for Post Qualification
Improvement of Barangay Road( Purok Antonio Siao to Purok Calumpang), Phase II, Barangay Big Margus | Barangay Big Margus | 5000000 |  |  | 0% |  |  | POW Preparation
Concreting of Barangay Road, Purok Cagang, Phase II, Barangay Tapon | Brgy. Tapon | 750000 |  |  | 0% |  |  | Contract Signing
Construction of Municipal Petroleum Depot/Station, Phase II, Barangay Poblacion | Barangay Poblacion | 210000 |  |  | 0% |  |  | POW Preparation
Construction of Tourism Facility (Tour Town Glan), Brgy. Kapatan | Brgy. Kapatan | 1000000 |  |  | 0% |  |  | Preparation of Master Plan
Concreting of Barangay Roads |  | 34881484.93 |  |  | 0% |  |  | 7/13 projects for public bidding
Ground preparation of Slaughterhouse Compound, Brgy. Taluya | Brgy. Taluya | 500000 |  |  | 0% |  |  | POW Preparation
Opening of Barangay Road (Sitio Kari to Sitio Gulo), Brgy. Small Margus | Brgy. Small Margus | 500000 |  |  | 0% |  |  | Procurement of Fuel
Completion of Tansition Resource Room with Complete Facilities |  | 500000 |  |  | 0% |  |  | bidded
Construction of Slaughterhouse and Amenities, Phase II, Brgy. Taluya | Brgy. Taluya | 3000000 |  |  | 0% |  |  | POW Preparation
Concreting of Municipal Roads |  | 10000000 |  |  | 0% |  |  | For issuance of Notice of Award
Total Economics Development Project |  | 119336393.6 |  |  |  | 4138898.37
Environmental Management
Total Environmental Management Project |  | 0
Grand Total |  | 124336393.6 |  |  |  | 4138898.37
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
|  | SGD |  |  |  | SGD
| ELENOR P. CORPUZ SGD |  |  |  | VICTOR JAMES B. YAP, SR. SGD
| Local Budget Officer |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43