## Form 4a - APP Office
FDP Form 4a - Annual Procurement Plan or Procurement List, by Office or Department
ANNUAL PROCUREMENT PLAN
REGION: | REGION XII - SOCCSSARGEN |  | CALENDAR YEAR: |  | 2026
PROVINCE: | SARANGANI
CITY/MUNICIPALITY: | GLAN
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? (Yes/No) | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Project)
[5 empty] | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO
300-2025-01-001 | Labor and Materials for the REPAIR OF DAMAGED EXISTING COVER COURT GYM @ BARANGAY TAPON, Barangay Tapon, Glan, Sarangani Province | Engineering | No | Public Bidding | January 17, 2025 | February 5, 2025 | May 5, 2025 | May 13, 2025 | Trust Fund | 918872.78 |  |  | Infra
300-2025-01-002 | Labor and Materials for the REPAIR OF DAMAGED EXISTING COVER COURT GYM @ BARANGAY SAN VICENTE, Barangay San Vicente, Glan, Sarangani Province | Engineering | No | Public Bidding | January 17, 2025 | February 5, 2025 | May 5, 2025 | May 13, 2025 | Trust Fund | 952530.53 |  |  | Infra
100-2025-01-0001 | Labor and Materials for the CONSTRUCTION OF BARANGAY HEALTH CENTER, PHASE-2, Barangay Laguimit, Glan, Sarangani Province | Engineering | No | Public Bidding | January 17, 2025 | February 5, 2025 | March 3, 2025 |  | General Fund | 500000 |  |  | Infra
100-2025-01-0002 | Labor and Materials for the CONSTRUCTION OF REINFORCED CONCRETE BOX CULVERT (TAPON – CONGAN ROAD) BARANGAY TAPON, Barangay Tapon, Glan, Sarangani Province | Engineering | No | Public Bidding | January 17, 2025 | February 5, 2025 | March 3, 2025 | March 14, 2025 | General Fund | 1300000 |  |  | Infra
100-2025-01-0003 | Labor and Materials for the INSTALLATION OF SOLAR –POWERED STREET LIGHTS, Barangay Taluya, Glan, Sarangani Province | Engineering | No | Public Bidding | January 17, 2025 | February 5, 2025 | March 3, 2025 | March 14, 2025 | General Fund | 1500000 |  |  | Infra
100-2025-01-0125 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, PUROK CAGANG, PHASE II, BRGY. TAPON, Barangay Tapon, Glan, Sarangani Province | Engineering | No | Public Bidding | January 17, 2025 | February 25, 2025 | March 18, 2025 | March 27, 2025 | General Fund | 750000 |  |  | Infra
100-2025-01-0165 | Labor and Materials for the THREE (3) PHASE LINE, GIT COMPOUND, BARANGAY CALABANIT, Barangay Calabanit, Glan, Sarangani Province | Engineering | No | Public Bidding | February 11, 2025 | March 4, 2024 | May 12, 2025 | May 23, 2025 | General Fund | 5000000 |  |  | Infra
100-2025-01-0164 | Labor and Materials for the CONCRETING OF BARANGAY ROADS, Glan, Sarangani Province | Engineering | No | Public Bidding | February 15, 2025 | March 6, 2024 | May 12, 2025 | May 23, 2025 | General Fund | 18587840.19 |  |  | Infra
100-2025-02-0241 | Labor and Materials for the CONCRETING OF MUNICIPAL ROAD, Datu Wata St., Barangay Poblacion, Glan, Sarangani Province | Engineering | No | Public Bidding | February 15, 2025 | March 6, 2024 | May 12, 2025 | May 23, 2025 | General Fund | 10000000 |  |  | Infra
100-2024-12-1625 | Supply and Delivery of Various Construction Materials to be used in the Improvement of RHU Dialysis Center RHU Compound in Barangay Poblacion, Glan, Sarangani Province | Engineering | No | Public Bidding | January 10, 2025 | January 29, 2025 | March 3, 2025 | March 10, 2025 | General Fund | 288604 |  |  | Goods
300-2024-12-093 | Supply and Delivery of Various Construction Materials to be used in the Improvement of Nursing Laboratory Room, GIT (Phase – 2) in Barangay Calabanit, Glan, Sarangani Province | Engineering | No | Public Bidding | January 10, 2025 | January 29, 2025 | March 3, 2025 | March 10, 2025 | Trust Fund | 1489155.5 |  |  | Goods
300-2024-12-095 | Supply and delivery of computer sets and accessories to be used by the different offices of the school and for the E-Laboratory of the different programs to be installed in GIT Campus, Brgy. Calabanit, Glan, Sarangani Province | Glan Institute of Technology | No | Public Bidding | January 10, 2025 | January 29, 2025 | October 15, 2025 | March 10, 2025 | Trust Fund | 795000 |  |  | Goods
100-2025-01-0023 | Supply and Delivery of Various Drugs and Medicines Supplies to be used for Children in the Conduct of Medical and Dental Outreach Program of RHU-Glan | Health Office | No | Public Bidding | January 25, 2025 | February 13, 2025 | March 18, 2025 | March 24, 2025 | General Fund | 425700 |  |  | Goods
100-2025-02-0246 | Supply and Delivery of Various Construction Materials to be used in the Improvement of Public Market (Comfort Room) in Barangay Poblacion, Glan, Sarangani Province | Engineering | No | Public Bidding | February 25, 2025 | March 18, 2025 | June 2, 2025 | June 13, 2025 | General Fund | 1017905 |  |  | Goods
100-2025-01-0296 | Supply and Delivery of 31 Units Radio Antenna Cable to be installed in 31 Barangays of Glan, Sarangani Province | MDRRMO | No | Public Bidding | March 4, 2025 | March 25, 2025 | May 13, 2025 | May 27, 2025 | General Fund | 2631528 |  |  | Goods
300-2025-02-014 | Supply and Delivery of Various Construction Materials to be used in the Improvement of Engineering Laboratory Room, GIT in Barangay Calabanit, Glan, Sarangani Province | Engineering | No | Public Bidding | March 4, 2025 | March 25, 2025 | May 13, 2025 | May 22, 2025 | Trust Fund | 711725.58 |  |  | Goods
300-2025-02-012 | One (1) year Subscription of Enterprise Resource Management – School Management System to be used by the faculty, staff and students of Glan Institute of Technology, GIT Campus, Barangay Calabanit, Glan, Sarangani Province | Glan Institute of Technology | No | Public Bidding | March 6, 2025 | March 26, 2025 | June 9, 2025 | June 17, 2025 | Trust Fund | 2000000 |  |  | Goods
100-2025-03- 0438 | Labor and Materials for the CONSTRUCTION OF LINED CANAL (JUNCTION NHW TO PUROK OSTIQUE), PHASE II, Barangay Big Margus, Glan, Sarangani Province | Engineering | No | Public Bidding | March 25, 2025 | April 15, 2025 | June 3, 2025 | June 11, 2025 | General Fund | 1000000 |  |  | Infra
100-2025-03- 0410 | Labor and Materials for the INSTALLATION OF SOLAR POWERED STREET LIGHTS, Barangay Kapatan, Glan, Sarangani Province | Engineering | No | Public Bidding | March 29, 2025 | April 22, 2025 | June 13, 2025 | July 21, 2025 | General Fund | 957000 |  |  | Infra
100-2025-03- 0411 | Labor and Materials for the INSTALLATION OF SOLAR POWERED STREET LIGHTS, Barangay Baliton, Glan, Sarangani Province | Engineering | No | Public Bidding | March 29, 2025 | April 22, 2025 | June 13, 2025 | July 21, 2025 | General Fund | 957000 |  |  | Infra
100-2025-03- 0412 | Labor and Materials for the INSTALLATION OF SOLAR POWERED STREET LIGHTS, Barangay Burias, Glan, Sarangani Province | Engineering | No | Public Bidding | March 29, 2025 | April 22, 2025 | June 13, 2025 | July 21, 2025 | General Fund | 957000 |  |  | Infra
100-2025-03- 0413 | Labor and Materials for the INSTALLATION OF SOLAR POWERED STREET LIGHTS, Barangay Batotoling, Glan, Sarangani Province | Engineering | No | Public Bidding | March 29, 2025 | April 22, 2025 | June 13, 2025 | July 21, 2025 | General Fund | 981000 |  |  | Infra
100-2025-03- 0414 | Labor and Materials for the INSTALLATION OF SOLAR POWERED STREET LIGHTS, Barangay Taluya, Glan, Sarangani Province | Engineering | No | Public Bidding | March 29, 2025 | April 22, 2025 | June 13, 2025 | July 21, 2025 | General Fund | 957000 |  |  | Infra
100-2025-03- 0415 | Labor and Materials for the INSTALLATION OF SOLAR POWERED STREET LIGHTS, Barangay Poblacion, Glan, Sarangani Province | Engineering | No | Public Bidding | March 29, 2025 | April 22, 2025 | June 13, 2025 | July 21, 2025 | General Fund | 888000 |  |  | Infra
100-2025-03- 0416 | Labor and Materials for the INSTALLATION OF SOLAR POWERED STREET LIGHTS, Barangay Big Margus, Glan, Sarangani Province | Engineering | No | Public Bidding | March 29, 2025 | April 22, 2025 | June 13, 2025 | July 21, 2025 | General Fund | 957000 |  |  | Infra
100-2025-03- 0405 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay Ilaya, Glan, Sarangani Province | Engineering | No | Public Bidding | April 11, 2025 | May 6, 2025 | July 14, 2025 | July 25, 2025 | General Fund | 2856790.4 |  |  | Infra
100-2025-03- 0406 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay Sufatubo, Glan, Sarangani Province | Engineering | No | Public Bidding | April 11, 2025 | May 6, 2025 | July 14, 2025 | July 25, 2025 | General Fund | 2856790.4 |  |  | Infra
100-2025-03- 0407 | Labor and Materials for the COMPLETION OF BARANGAY HEALTH STATION, BRGY. CONGAN, Barangay Congan, Glan, Sarangani Province | Engineering | No | Public Bidding | April 11, 2025 | May 6, 2025 | July 11, 2025 | July 21, 2025 | General Fund | 700000 |  |  | Infra
100-2025-03- 0408 | Labor and Materials for the CONSTRUCTION OF MULTI-PURPOSE BUILDING (COVER COURT), PHASE II, D. CANIA MES, Barangay Tapon, Glan, Sarangani Province | Engineering | No | Public Bidding | April 11, 2025 | May 6, 2025 | July 11, 2025 | July 21, 2025 | General Fund | 2500000 |  |  | Infra
100-2025-03- 0409 | Labor and Materials for the COMPLETION OF BARANGAY HEALTH STATION, BRGY. TAPON, Barangay Tapon, Glan, Sarangani Province | Engineering | No | Public Bidding | April 11, 2025 | May 6, 2025 | July 11, 2025 | July 21, 2025 | General Fund | 700000 |  |  | Infra
100-2025-03- 0495 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay San Vicente, Glan, Sarangani Province | Engineering | No | Public Bidding | April 11, 2025 | May 6, 2025 | July 14, 2025 | July 25, 2025 | General Fund | 2856790.4 |  |  | Infra
100-2025-03- 0496 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay Batulaki, Glan, Sarangani Province | Engineering | No | Public Bidding | April 11, 2025 | May 6, 2025 | July 14, 2025 | July 25, 2025 | General Fund | 2856790.4 |  |  | Infra
100-2025-04-0535 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay Lago, Glan, Sarangani Province | Engineering | No | Public Bidding | May 3, 2025 | May 22, 2025 | July 14, 2025 | July 25, 2025 | General Fund | 2856790.4 |  |  | Infra
100-2025-04-0572 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay Tango, Glan, Sarangani Province | Engineering | No | Public Bidding | May 24, 2025 | June 17, 2025 | August 1, 2025 | August 11, 2025 | General Fund | 2856790.4 |  |  | Infra
100-2025-04-0573 | Labor and Materials for the CONSTRUCTION OF BREASTFEEDING ROOM, @ RHU COMPOUND, Barangay Poblacion, Glan, Sarangani Province | Engineering | No | Public Bidding | May 24, 2025 | June 17, 2025 | July 14, 2025 | July 25, 2025 | General Fund | 750000 |  |  | Infra
100-2025-04-0580 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay Cross, Glan, Sarangani Province | Engineering | No | Public Bidding | May 24, 2025 | June 17, 2025 | August 1, 2025 | August 11, 2025 | General Fund | 2856790.4 |  |  | Infra
100-2025-01-0021 | Supply and delivery of 6,611 liters Diesel and Lubricants for fuel consumption and lubricants of RP Heavy Equipment to be used in the Opening of Brgy. Road (Sitio Kari to Sitio Gulo), Brgy. Small Margus, Glan, Sarangani Province | Engineering | No | Negotiated Bidding | March 22, 2025 | March 31, 2025 | July 18, 2025 | September 8, 2025 | General Fund | 499769.6 |  |  | Goods
100-2025-03-0459 | Rental of Lights & Sounds System for 3 days to be used in the celebration of 2025 Mahin Festival on April 24-26, 2025 in Brgy. Gumasa, Glan, Sarangani Province | Mayor's Office | No | Public Bidding | March 25, 2025 | April 15, 2025 | April 21, 2025 | April 23, 2025 | General Fund | 500000 |  |  | Goods
300-2025-03-023 | Supply and Delivery of Various Furniture to be used and installed in the Office of the Director of Student Affairs and Services (DSAS) in GIT Campus, Brgy. Calabanit, Glan, Sarangani Province | Glan Institute of Technology | No | Public Bidding | April 4, 2025 | April 24, 2025 | May 21, 2025 | June 24, 2025 | Trust Fund | 355200 |  |  | Goods
100-2025-03-0402 | Supply and Delivery of Various Drugs and Medicines Supplies to be used in Non-Communicable Disease Prevention Program of RHU-Glan | Health Office | No | Public Bidding | April 4, 2025 | April 24, 2025 | May 21, 2025 | July 2, 2025 | General Fund | 599920 |  |  | Goods
100-2025-03-0442 | Supply and Delivery of Various Drugs and Medicines Supplies to be used in Maternal & Child Health Care Program of RHU-Glan | Health Office | No | Public Bidding | April 4, 2025 | April 24, 2025 | May 21, 2025 | June 2, 2025 | General Fund | 501600 |  |  | Goods
100-2025-03-0444 | Supply and Delivery of Anti-Rabies Vaccine to be used in Rabies Prevention and Control Program of RHU-Glan | Health Office | No | Public Bidding | April 4, 2025 | April 24, 2025 | May 21, 2025 | June 2, 2025 | General Fund | 599940 |  |  | Goods
100-2025-05-0732 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay Congan, Glan, Sarangani Province | Engineering | No | Public Bidding | June 21, 2025 | July 15, 2025 | August 1, 2025 | August 11, 2025 | General Fund | 2856790.4 |  |  | Infra
100-2025-06-0780 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay Baliton, Glan, Sarangani Province | Engineering | No | Public Bidding | June 21, 2025 | July 15, 2025 | August 1, 2025 | August 11, 2025 | General Fund | 600000.13 |  |  | Infra
100-2025-06-0797 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay Rio Del Pilar, Glan, Sarangani Province | Engineering | No | Public Bidding | June 21, 2025 | July 15, 2025 | August 1, 2025 | August 11, 2025 | General Fund | 2856790.4 |  |  | Infra
100-2025-06-0827 | Labor and Materials for the IMPROVEMENT OF BARANGAY ROAD (PUROK ANTONIO SIAO TO PUROK CALUMPANG) PHASE II, Barangay Big Margus, Glan, Sarangani Province | Engineering | No | Public Bidding | July 4, 2025 | July 24, 2025 | August 18, 2025 | August 29, 2025 | General Fund | 5000000 |  |  | Infra
100-2025-07-1043 | Labor and Materials for the ROAD CONSTRUCTION / OPENING / REHABILITATION / IMPROVEMENT, Barangay Cablalan, Glan, Sarangani Province | Engineering | No | Public Bidding | July 31, 2025 | August 20, 2025 | September 25, 2025 | October 15, 2025 | General Fund | 2246900 |  |  | Infra
300-2025-08-092 | Labor and Materials for the CONSTRUCTION OF FLOOD CONTROL, Barangay Ilaya, Glan, Sarangani Province | Engineering | No | Public Bidding | August 9, 2025 | August 28, 2025 | September 25, 2025 | October 15, 2025 | Trust Fund | 5841577.05 |  |  | Infra
100-2025-08-1146 | Labor and Materials for the FENCING OF GIT COMPOUND PHASE II, BRGY. CALABANIT, GIT Compound, Barangay Calabanit, Glan, Sarangani Province | Engineering | No | Public Bidding | August 30, 2025 | September 23, 2025 | October 15, 2025 | October 23, 2025 | General Fund | 5000000 |  |  | Infra
300-2025-03-020 | Supply and Delivery of 1 Unit BeneHeart D30 to be used in Dialysis Center, Barangay Poblacion, Glan, Sarangani Province | Health Office | No | Public Bidding | April 3, 2025 | July 1, 2025 | August 1, 2025 | August 11, 2025 | Trust Fund | 370000 |  |  | Goods
300-2025-03-021 | Supply and Delivery of Various Dental Supplies to be used in RHU-Glan | Health Office | No | Public Bidding | April 3, 2025 | July 1, 2025 | August 1, 2025 | August 11, 2025 | Trust Fund | 348700 |  |  | Goods
100-2025-03-0446 | Supply and Delivery of 5,815 liters Diesel for Fuel Consumption of RP Heavy Equipment to be used in the REHAB/IMPROVEMENT OF BARANGAY ROAD in Barangay Calpidong, Glan, Sarangani Province | Engineering | No | Public Bidding | June 3, 2025 | July 1, 2025 | August 1, 2025 | August 6, 2025 | General Fund | 482645 |  |  | Goods
300-2025-02-016 | Supply and delivery of 16 units brand new wall mounted aircon and other materials to be used and installed in the different classrooms in Glan Institute of Technology, Brgy. Calabanit, Glan, Sarangani Province | Glan Institute of Technology | No | Public Bidding | June 3, 2025 | July 1, 2025 | August 1, 2025 | August 6, 2025 | Trust Fund | 679237 |  |  | Goods
100-2025-05-0708 | Supply and Delivery of Various Construction Materials to be used in the FABRICATION AND INSTALLATION OF PRE-CAST CONCRETE COVER at Barangay Poblacion, Glan, Sarangani Province | Engineering | No | Public Bidding | June 21, 2025 | July 15, 2025 | August 1, 2025 | August 19, 2025 | General Fund | 214173.2 |  |  | Goods
100-2025-06-0883 | Rental of Lights & Sounds System for 5 days to be used in the celebration of 76th Foundation Anniversary on July 23-27, 2025 in Glan, Sarangani Province | Mayor's Office | No | Public Bidding | June 26, 2025 | July 16, 2025 | July 21, 2025 | July 22, 2025 | General Fund | 1000000 |  |  | Goods
100-2025-05-0667 | Supply and Delivery of Various Dental Supplies to be used in RHU-Glan | Health Office | No | Public Bidding | June 14, 2025 | July 16, 2025 | September 25, 2025 | October 16, 2025 | General Fund | 508670 |  |  | Goods
100-2025-05-0689 | Supply and Delivery of 6,810 liters Diesel and Lubricants for fuel consumption and lubricants of RP Heavy Equipment to be used in the Ground Preparation of Slaughterhouse Compound at Barangay Taluya, Glan, Sarangani Province | Engineering | No | Public Bidding | May 30, 2025 | July 16, 2025 | August 18, 2025 | September 2, 2025 | General Fund | 500000 |  |  | Goods
100-2025-06-0855 | Supply and Delivery of Various Construction Materials to be used in the construction of 50 temporary houses for resettlement of fire-affected families | MDRRMO | No | Public Bidding | July 4, 2025 | July 24, 2025 | August 5, 2025 | August 27, 2025 | General Fund | 489600 |  |  | Goods
300-2025-06-070 | Supply and Delivery of Anti-Rabies Vaccine to be used in Rabies Prevention and Control Program of RHU-Glan | Health Office | No | Public Bidding | July 15, 2025 | August 5, 2025 | August 18, 2025 | September 1, 2025 | Trust Fund | 599940 |  |  | Goods
300-2025-07-080 | Supply and Delivery of Various Drugs and Medicines Supplies to be used in the Conduct of Daily Consultation for adults at the Super Health Center, Barangay Poblacion, Glan, Sarangani Province | Health Office | No | Public Bidding | July 15, 2025 | August 5, 2025 | August 18, 2025 | September 1, 2025 | Trust Fund | 503330 |  |  | Goods
100-2025-08-1088 | Supply and Delivery of Various Construction and Plumbing Materials to be used in the Provision of Temporary Shelter (Resettlement of Fire Affected Families), at Barangay Taluya, Glan, Sarangani Province | Engineering | No | Public Bidding | August 9, 2025 | August 28, 2025 | September 25, 2025 | October 13, 2025 | General Fund | 932132.4 |  |  | Goods
100-2025-08-1097 | Supply and Delivery of 1 Unit Brand New Inflatable Boat with Engine and Trailer to be used by the coast guard personnel in monitoring the municipal sea water and coast line boundaries in the Municipality of Glan, Sarangani Province | Mayor's Office | No | Public Bidding | August 15, 2025 | September 4, 2025 | September 25, 2025 | October 14, 2025 | General Fund | 800000 |  |  | Goods
300-2025-08-095 | Supply and Delivery of Various Drugs and Medicines Supplies to be used in the Daily Consultation at the Super Health Center, Barangay Poblacion, Glan, Sarangani Province | Health Office | No | Public Bidding | August 29, 2025 | September 23, 2025 | October 15, 2025 | October 27, 2025 | Trust Fund | 881130 |  |  | Goods
100-2025-09-1193 | Rental of Lights & Sound System for 10 days to be used in the celebration of 26th Lubi-Lubi Festival in Glan, Sarangani Province from September 29, 2025 to October 08, 2025 | Mayor's Office | No | Public Bidding | September 4, 2025 | September 24, 2025 | September 29, 2025 | September 29, 2025 | General Fund | 1300000 |  |  | Goods
100-2025-09-1207 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay Calpidong, Glan, Sarangani Province | Engineering | No | Public Bidding | September 20, 2025 | October 10, 2025 | November 10, 2025 | November 19, 2025 | General Fund | 2856790.4 |  |  | Infra
100-2025-09-1208 | Labor and Materials for the CONCRETING OF BARANGAY ROAD, Barangay New Aklan, Glan, Sarangani Province | Engineering | No | Public Bidding | September 20, 2025 | October 10, 2025 | November 10, 2025 | November 19, 2025 | General Fund | 2856790.4 |  |  | Infra
100-2025-08-1091 | Labor and Materials for the CONSTRUCTION OF SLOPE PROTECTION, PUROK DURANTA, BRGY. TALUYA, Barangay Taluya, Glan, Sarangani Province | Engineering | No | Public Bidding | August 15, 2025 | October 14, 2025 | December 22, 2025 | January 22, 2026 | General Fund | 500000 |  |  | Infra
100-2025-10-1385 | Labor and Materials for the CONSTRUCTION / OPENING OF LOCAL ROAD @ SITIO NIBONG, Barangay Cablalan, Glan, Sarangani Province | Engineering | No | Public Bidding | October 16, 2025 | November 5, 2025 | December 12, 2025 | December 22, 2025 | General Fund | 1611643.49 |  |  | Infra
300-2025-08-102 | Supply and Delivery of Various Drugs and Medicines Supplies to be used in the Conduct of Daily Consultation for children at the Super Health Center, Barangay Poblacion, Glan, Sarangani Province | Health Office | No | Public Bidding | September 30, 2025 | October 21, 2025 | December 12, 2025 | December 18, 2025 |  | 623106 |  |  | Goods
300-2025-09-104 | Supply and Delivery of Anti-Rabies Vaccine to be used in Rabies Prevention and Control Program of RHU-Glan | Health Office | No | Public Bidding | September 30, 2025 | October 21, 2025 | December 12, 2025 | December 18, 2025 | Trust Fund | 599940 |  |  | Goods
300-2025-09-111 | Supply and Delivery of Various Drugs and Medicines Supplies to be used in the Daily Maintenance Medicines for HPN/DM Patients for 31 Barangays of Glan, Sarangani Province | Health Office | No | Public Bidding | September 30, 2025 | October 21, 2025 | December 12, 2025 | December 18, 2025 | Trust Fund | 698600 |  |  | Goods
300-2025-09-117 | Supply and Delivery of Various Materials and Equipment to be used in the Criminology Laboratory Department of GIT, Brgy. Calabanit, Glan, Sarangani Province | Glan Institute of Technology | No | Public Bidding | September 30, 2025 | October 21, 2025 | December 12, 2025 | January 5, 2026 | Trust Fund | 569619 |  |  | Goods
100-2025-10-1387 | Supply and Delivery of 6,430 liters Diesel Fuel and Lubricants for fuel consumption and lubricants of RP Heavy Equipment to be used in the Construction / Opening of Barangay Road @ Purok Kalsidao to Purok Alna, Barangay Pangyan, Glan, Sarangani Province | Engineering | No | Public Bidding | October 16, 2025 | November 5, 2025 | December 12, 2025 | January 5, 2026 | General Fund | 499540.31 |  |  | Goods
300-2025-11-141 | Supply and Delivery of Various Drugs and Medicines Supplies to be used for children in the conduct of Medical and Dental Outreach Program of RHU-Glan & conduct of Daily Consultation at the Super Health Center, Barangay Poblacion, Glan, Sarangani Province | Health Office | No | Public Bidding | November 25, 2025 | December 16, 2025 | January 13, 2026 | January 30, 2026 | Trust Fund | 715536 |  |  | Goods
300-2025-11-142 | Supply and Delivery of Various Drugs and Medicines Supplies to be used in the conduct of Medical and Dental Outreach Program of RHU-Glan & conduct of Daily Consultation at the Super Health Center, Barangay Poblacion, Glan, Sarangani Province | Health Office | No | Public Bidding | November 25, 2025 | December 16, 2025 | January 13, 2026 | January 30, 2026 | Trust Fund | 3722250 |  |  | Goods
300-2025-11-144 | Supply and Delivery of Various Drugs and Medicines to be used in the conduct of Mental Health Program of RHU-Glan | Health Office | No | Public Bidding | November 25, 2025 | December 16, 2025 | January 13, 2026 | January 29, 2026 | Trust Fund | 1764050 |  |  | Goods
300-2025-11-145 | Supply and Delivery of Various Drugs and Medicines Supplies to be used in the Non-Communicable Disease Prevention Program of RHU-Glan | Health Office | No | Public Bidding | November 25, 2025 | December 16, 2025 | January 13, 2026 | January 30, 2026 | Trust Fund | 1091350 |  |  | Goods
300-2025-11-146 | Supply and Delivery of Various Medicines to be used in National Tuberculosis Program for adults of RHU-Glan | Health Office | No | Public Bidding | November 25, 2025 | December 16, 2025 | January 13, 2026 | January 30, 2026 | Trust Fund | 1162800 |  |  | Goods
300-2025-11-147 | Supply and Delivery of Various Vaccines to be used for Rabies Control Program of RHU-Glan | Health Office | No | Public Bidding | November 25, 2025 | December 16, 2025 | January 13, 2026 | January 30, 2026 | Trust Fund | 1488375 |  |  | Goods
This is to certify that the above procurement plan is in accordance with the objective of this Office.
Prepared by: |  |  |  |  | Approved by:
|  | SGD |  |  |  | SGD
|  | GEORGE S. ALCUDIA |  |  |  | VICTOR JAMES B. YAP SR.
| BAC CHAIRMAN |  |  |  | M unicipal Mayor

## data validation (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
Emergency Procurement under the Bayanihan Act
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets
Others - Foreign-funded procurement

## Form 4b - APP Summary
FDP Form 4b - Annual Procurement Plan or Procurement List, Summary
ANNUAL PROCUREMENT PLAN SUMMARY
REGION: | REGION XII - SOCCSSARGEN | CALENDAR YEAR: | 2026
PROVINCE: | SARANGANI
CITY/MUNICIPALITY: | GLAN
Summary by Office
Department | Head of Department / Office | Total Cost
MAYOR'S OFFICE | VICTOR JAMES B. YAP, SR. | 3600000
VICE MAYORS'S OFFICE | VICTOR JAMES P. YAP, JR.
LEGAL | ATTY. CLEMENTE A. PANGANDUYON
ADMIN | PATRICK S. YAP
ENGINEERING | ENGR. JOSE JERRY BALTAZAR | 110673709.2
OMAG/DA | VIRGINIA MUSA
MPDO | ENGR. ERIC PAGARAN
ACCOUNTING | MARLETTE R. ENGKONG
BUDGET | ELENOR CORPUZ
LOCAL CIVIL REGISTRY | ESTHER L. CARTEN
MLGOO | MARIA FRITZIE A. ESPANOL
ASSESSOR | ATTY. ARVEL S. LARA
MTO | RONELIO L. FLORES
TOURISM | RHOA D. WADINGAN
GSO | ENGR. JORGE S. ALCUDIA
BAC | ENGR. JORGE S. ALCUDIA
MENRO | MAYETTE B. ORCULLO
MCTC | EDITHA SATURA
SB SECRETARIAT | MARLON S. DAQUIGAN
MDRRMO | ANTONIO R. ACHARON | 3121128
BFP | SFO3 RONILLO S. BARSUMO
PNP | PTCOL JOVENSON BAYONA
HR | DAVE NICK D. BESANA
HEALTH | DR. JOSE RIGEL SANTOS | 17204937
MARKET | ALBERTO PASAPORTE JR.
MSWD | MARY JOY P. GALLAZA
COMELEC | GERTRUDES S. OMAÑA
GIT | DR. NESTOR P. BLACE | 4399056
PESO | DAVE NICK D. BESANA
VETERINARY OFFICE | VERNIE RINO L. ASPERGA
138998830.2
Prepared By: |  | Approved By:
| SGD | SGD
GEORGE S. ALCUDIA |  | VICTOR JAMES B. YAP SR.
Head, BAC Secretariat |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v4
45